## Risks
Risk | Mitigation | Priority | Impact | Urgency
Data Security and Privacy Risks: Sensitive data might be exposed to vulnerabilities during and after migration. | o Use data encryption both in transit and at rest. Work and integrate with security team to understand the encryption use cases o Implement strict access controls and conduct regular audits. o Ensure compliance with relevant regulations like GDPR | High | High | High
Downtime and Service Interruptions: Services may be disrupted, affecting user experience and business operations. | o Schedule migration during low-traffic periods and plan for rollback. o Use hybrid or phased migration approaches to minimize impact. o Test thoroughly in a staging environment before going live. o Work with the development team to recognize off peak periods and inform the customers accordingly | High | High | High
Cost Overruns: Unexpected costs due to additional resources, bandwidth, or underestimating storage needs. | o Perform a thorough cost analysis, including all anticipated services and resources. o Set up automated budget alerts and track cloud usage in real-time. o Optimize cloud resource allocation post-migration and review regularly. o Cost analyzer tool in AWS to send updates and reminders about usage costs. | Medium | Medium | Medium
Data Loss or Corruption: Data may be lost, corrupted, or inaccessible during migration. | o Back up all data before migration and verify backup integrity. o Use automated tools to detect and prevent data inconsistencies. o Implement continuous monitoring and validation checks during data transfer. o Do checksums and roll backs if necessary o Set up DR | High | High | High
Integration Issues: Compatibility issues with legacy systems or third-party applications may arise. | o Conduct a compatibility assessment of existing applications with the new cloud environment. o Use API management tools for seamless integration of disparate systems. o Involve development teams early to plan for necessary modifications. | Medium | Medium | Medium
Performance Degradation: Applications may not perform as efficiently in the cloud as they did on-premises. | o Benchmark current performance and set cloud performance SLAs. o Implement autoscaling and load-balancing capabilities to handle high loads. o Optimize application architecture and code for cloud environments. | Medium | Medium | Medium
Compliance and Regulatory Risks: Migrating data to the cloud may lead to non-compliance with industry regulations. | o Review and understand regulatory requirements for data in cloud storage. Work with legal team to understand the gaps o Choose cloud providers that meet relevant compliance standards. o Conduct a compliance audit post-migration and ensure data governance. | High | High | Medium
Skills Gap in Cloud Technology: Lack of in-house cloud expertise could lead to delays and errors. | o Train existing staff on cloud technologies and best practices. o Consider hiring consultants or partnering with managed service providers. o Build a cloud center of excellence within the organization for guidance and support. | Medium | Medium | Medium
Project Scope Creep:The migration project may expand beyond the initial scope, increasing complexity and timelines. | o Define clear goals and deliverables for the project with a change management process. o Use agile project management methodologies for regular check-ins and adjustments. o Ensure stakeholders agree on priorities to limit unnecessary feature requests. | Medium | Medium | Low

## FAQ
High Priority: Risks that could significantly jeopardize the migration’s success (e.g., security, downtime, data loss, compliance).
Medium Priority: Risks that can be managed during migration but still require significant attention (e.g., cost, performance, skills gap).
Low Priority: Risks that are less likely to affect immediate migration outcomes but could pose long-term challenges (e.g., vendor lock-in).
High Impact: Risks that, if materialized, could have major business or operational consequences.
Medium Impact: Risks that could cause moderate disruptions or additional costs.
Low Impact: Risks with minimal consequences.
High Urgency: Risks that require proactive planning and resolution before or during the migration.
Medium Urgency: Risks that can be managed during or shortly after migration.
Low Urgency: Risks that can be addressed later without significant impact on migration progress.