## Checklist
Launch Checklist
Team | Requirement | Action
Data, Application and Analytics team | Data Integrity and Validation | Verify that all analytics data is accurately migrated, including historical data and reports.
Conduct integrity checks to ensure data quality and consistency post-migration.
Testing Analytics Platforms and Dashboards
Test all dashboards, reporting tools, and integrations to confirm they function as expected.
Ensure real-time data flows smoothly from sources to dashboards without delays or data loss.
Development Team | Performance Benchmarking | Benchmark analytics processing times before and after migration to ensure cloud performance meets expectations.
| User Access and Permissions | Review and assign access permissions for analytics teams, ensuring data security and compliance.
Confirm access levels are set according to roles and that data remains protected.
Review and assign access permissions for analytics teams, ensuring data security and compliance.
Confirm access levels are set according to roles and that data remains protected.
Sales | Verify customer data | Test customer tracking, and forecasting tools in the cloud environment to verify functionality.
| Data Accuracy for Customer Records | Check that customer data has migrated without loss, duplication, or formatting errors.
| Training | Test sales performance dashboards and reporting tools for real-time data accuracy and availability.
| Reporting | Conduct training sessions for the sales team on accessing and using the cloud environment.
Marketing | Marketing Automation Platform Testing | Test Marketing data flows between cloud and Platforms
Verify content and access management
Verify web analytics is performing as expected
Campaign data validation if available
Content and Asset management data validation if available
Customer success | Customer Support Tools Testing | Test Customer Support Tools Testing for functionality and testing. Ensure that customer case histories, and interactions are intact
| Knowledge Base and Resources Accessibility | Verify that knowledge bases, FAQs, and self-service resources are accessible and correctly migrated.
| Customer Data Security and Privacy | Review access controls to ensure only authorized customer success team members can view sensitive data. Validate that customer data complies with security and privacy standards in the cloud
| System Performance During Peak Times | Test system response times during simulated peak periods to ensure stability for customer-facing functions. Conduct load testing for applications critical to customer support and interactions.
Product Marketing | Product Data and Documentation Validation | Ensure all product-related data and documentation (datasheets, product roadmaps) are accurately migrated.
Confirm that product marketing collateral is accessible and correctly formatted.
| User Feedback and Product Metrics | Verify integration with user feedback tools and product metrics dashboards post-migration.
Validate that product metrics are accurately reflected for insights on customer usage and engagement.
| Feature Usage Analytics | Confirm that product usage analytics data flows seamlessly and accurately to support insights into feature adoption and user engagement.
Test dashboards for product insights to verify their accuracy and real-time functionality.
Risk | Security and Compliance Verification | Review all security configurations, including encryption, access controls, and data masking.
| Audit Logs and Monitoring Setup | Ensure audit logs are set up for tracking data access, changes, and system alerts.
Set up real-time monitoring and alerts for unauthorized access or unusual activity.
| Data Backup and Recovery Validation | Verify that data backups are functioning correctly and are accessible in case of a data loss incident.
Test recovery procedures for critical data to validate disaster recovery readiness.
| Vulnerability Testing and Remediation | Conduct penetration testing and vulnerability scans on the cloud environment.
Document any identified vulnerabilities and verify remediation measures.
Legal | Data Residency and Jurisdiction Compliance | Confirm that all data is stored in approved locations to comply with data residency regulations.
Verify that cloud provider contracts address data handling and storage location compliance
| Access Control and Privacy Policies | Review access control configurations to ensure adherence to privacy laws and internal data governance policies.
Confirm that privacy policies are updated to reflect the new cloud environment.
| Intellectual Property Protection | Validate that intellectual property (IP) data and sensitive assets are adequately protected and access-controlled in the cloud.
Confirm compliance with IP protection regulations and internal standards.
IT/Operations | Infrastructure Validation | Check that cloud infrastructure (network, compute, storage) aligns with the BU requirements.
| Performance and Load Testing | Conduct system-wide performance and load tests to ensure stability and responsiveness.
| Disaster Recovery and Backup | Verify that backup and disaster recovery configurations are functional and meet BUs’ data protection needs.
| Monitoring and Support Setup | Establish ongoing support channels and monitoring tools to provide assistance post-launch.

## Final go live checklist
This is across all functions/all BU
Requirement | Action
End to end testing | Conduct final end-to-end tests across applications, integrations, and workflows for all departments to confirm seamless operation in the cloud.
Communication and Change management
Communicate the migration timeline, status, and support resources to all teams.
Provide guidance on reporting issues post-migration and any expected system downtimes.
User training and Support | Offer training sessions and support resources for users, focusing on any changes in workflows, tools, or interfaces.
Final stakeholder Sign off | Set up a support channel for post-migration troubleshooting.
Obtain final sign-off from each department, confirming that their requirements have been met and systems are fully operational.
Confirm that all stakeholders have reviewed and approved the post-migration environment.
Contingency and Rollback Plan | Confirm that contingency and rollback plans are in place should any critical issues arise.